## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME: | Full Stack Web Development (MERN)
INTERN NAME: | Anuj Tiwari
PROJECT NAME: | PathPort – Professional Networking Platform for Higher Education Students
DOCUMENT NAME: | Lessons Learnt Log
CREATED ON: | 2026-05-02
Purpose of Document
Lessons Learned Logs are used to capture and share knowledge about what has worked well and what could have been done differently during the planning, management and delivery of an improvement project.
They help others learn from the project team's experience. Lesson Learned Logs: Help support a learning culture.
INSTRUCTIONS:
1. Text in Italics are instructions for completing the document
2. Text in orange is just for reference and should be deleted before submitting the document
3. Comments may be added to some of the cells, please read the comments to better understand the terms
4. All fields must be duly filled
5. The descriptions for what to be filled in each of the fields are provided in the template.
6. Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes.

## LESSONS LEARNED
LESSONS LEARNED
DOCUMENT VERSION: 1.0
PROJECT NAME | PathPort – Professional Networking Platform for Higher Education Students |  |  |  | PLEASE GO THROUGH THE INSTRUCTION SHEET PROVIDED TO GET AN UNDERSTANDING OF HOW TO USE THIS TEMPLATE.
PROJECT ID | IP-11182
PROJECT MANAGER | Cloud Counselage GPI Mentor
PROJECT SPONSOR | Cloud Counselage Pvt. Ltd. – Industry Academia Community (IAC)
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
1 | 2026-04-22 | Login was failing on deployed environment because JWT cookie and CORS were not configured correctly. | Technical / Environment | Yes – CORS and cookie warnings were visible in browser console during early tests. | Configure CORS and cookie settings for production at the start of the project and verify them in a staging deployment. | Reviewed network requests, updated CORS config, allowed credentials and correct CLIENT_ORIGIN in backend, reconfigured cookies on Render and Vercel, then re-tested. | Anuj Tiwari | Solved | Created a small deployment checklist to avoid missing CORS/JWT settings in future.
2 | 2026-04-26 | MongoDB models changed multiple times in the middle of development, causing data inconsistency and code refactoring. | Requirements / Design | Yes – frequent new fields were being added to User and Job models. | Freeze the core database schema earlier by preparing an ERD / model document and validating it against requirements before heavy coding. | Documented all main models in the README (Database Architecture section), avoided non-critical schema changes afterwards and cleaned up old data. | Anuj Tiwari | Solved | For future projects, consider using migration scripts when the schema must change.
3 | 2026-04-27 | Initial testing was ad-hoc because formal test cases and RTM were not prepared at the beginning. | Process / Testing | No – issues became clear only when features increased and it was hard to remember all scenarios. | Create a Test Plan, RTM and list of test cases before full-scale execution so that coverage can be tracked. | Prepared detailed Test Plan, Requirement Traceability Matrix and functional test cases Excel, then re-executed tests systematically. | Anuj Tiwari | Solved | Structured testing increased confidence in the stability of PathPort.
4 | 2026-04-29 | Time required for integrating OpenAI (Jarvis AI and Career Translator) was underestimated. | Planning / Estimation | Yes – unfamiliarity with OpenAI SDK and prompt design was known from the start. | For any new technology, plan a small spike/POC early and keep additional buffer time in the schedule. | Built a minimal POC for one Jarvis mode, then extended it; simplified some AI features and implemented offline fallback logic to control scope. | Anuj Tiwari | Solved | Next projects will explicitly include POC tasks during planning.
5 | 2026-04-29 | As more features were added, some pages became cluttered and difficult to navigate (especially student dashboard). | UI/UX Design | Yes – long forms and multiple sections started appearing on single screens. | Plan the information architecture and navigation flow early; use separate pages and tabs for complex modules. | Refactored UI into focused pages such as SkillMapPage, PortfolioPage, AiJarvisPage; reused MUI components and consistent dark theme. | Anuj Tiwari | Solved | User experience became cleaner and easier to demo.
6 | 2026-04-30 | Creating test data manually (users, jobs, applications) was taking a lot of time for each new environment. | Productivity / Test Data | Yes – repeated manual sign-ups and job postings were required during early tests. | Create automated seeding scripts and standard demo accounts at the start of testing. | Developed seed.js script to insert demo student, recruiter, mentor accounts, jobs, evidence cards and skill nodes; reused it whenever DB was reset. | Anuj Tiwari | Solved | Seeding saved time and made it easy to run consistent end-to-end scenarios.