## GPI - Project Charter
PROJECT CHARTER
GENERAL PROJECT INFORMATION
PROJECT NAME | PathPort – Professional Networking Platform for Higher Education Students
PROJECT SPONSOR | Tushar Topale
PROJECT MANAGER | Harshada Topale
EXPECTED START DATE | 2026-05-15
EXPECTED COMPLETION DATE | 2026-05-05
ESTIMATED COST | N.A.
GOALS, OBJECTIVES, DELIVERABLES
PROJECT OBJECTIVE (Objective of a project represents the output or what you want to accomplish by doing it.) | To develop a full-stack MERN web application that provides a professional networking, job/internship platform, mentorship system, and AI-based career guidance for students.
BUSINESS CASE (A business case provides justification for undertaking a project. It evaluates the benefit, cost and risk of alternative options and provides a rationale for the preferred solution. ) | Current platforms like LinkedIn are generic. PathPort provides a specialized ecosystem for students to track continuous growth and prove skills with real evidence.
GOALS/METRICS (The project goal refers to achieving a desired outcome (performance goal) at a specific end date (time goal) employing a specific amount of resources (resource goal).) | 100% completion of core modules (Student/Recruiter/Mentor) and successful integration of AI Jarvis and Skill Map within 120 hours.
EXPECTED DELIVERABLES (Describe the quantifiable goods or services that must be provided upon the completion of a project.) | Full Source Code (GitHub), Live Deployment Link, Project Report, Video Walkthrough, and Presentation (PPT).
PROJECT SCOPE AND SCHEDULE
WITHIN SCOPE (This is functions and information which should be taken into account(estimated) in the development at the first stage. Or the stage for the development perios.) | • Development of a MERN‑based web application (React + Node.js + Express + MongoDB). • Implementation of three roles: – Student: profile, Skill Map, Evidence Portfolio, Journal, job search & apply, applications tracking. – Recruiter: company profile, job/internship posting, recruiter dashboard, applicant view and pipeline management. – Mentor: mentor profile, mentorship offers, mentorship sessions and feedback. • AI‑assisted features: – Jarvis‑style AI assistant for career guidance. – Career Translator to convert casual descriptions into professional résumé bullets. • Core networking: – Connections, 1‑to‑1 messaging, basic social feed. • Deployment: – Backend on Render, frontend on Vercel, database on MongoDB Atlas. – Configuration using environment variables without hardcoding secrets. • Documentation, testing and submission of all required GPI deliverables.
OUTSIDE OF SCOPE (This is functions which are planned to be done, but they are not reqired on the first stages.) | • Native mobile applications (Android/iOS) for PathPort. • Integration with payment gateways or paid mentorship plans. • Deep analytics dashboards for colleges/universities and recruiters. • Real‑time video/voice calling features within the platform. • Advanced recommendation engine using ML (beyond basic AI prompts). • Enterprise multi‑tenant configuration for multiple institutions. These items are considered future enhancements and are not planned in the first 120‑hour internship implementation.
PROJECT RESOURCES AND COSTS
PROJECT TEAM (Mention the number of resources, who will be working on the project.) | • 1 Full‑Stack Developer (Intern): Anuj Tiwari – Responsible for requirements understanding, design, frontend, backend, database, deployment, testing and documentation. The project is executed as an individual internship project; no additional developers are planned.
SUPPORT RESOURCES (Mention all the other resources that will be needed for the completion of the project.) | • Project Sponsor: Tushar Topale (Cloud Counselage) • Project Manager / Domain Lead: Harshada Topale (Cloud Counselage) • GPI mentors and evaluation team for guidance and feedback. • Tools and platforms: – Visual Studio Code, Git & GitHub, – MongoDB Atlas (free tier), – Render (backend hosting, free tier), – Vercel (frontend hosting, free tier), – Postman / browser dev tools for API testing.
COST ALLOCATION (Mention the cost of all the resources on an hourly/monthly/yearly basis. This will help to stick on to the project budget.) | No direct monetary cost is allocated for this project. • Development effort is provided by the intern (approx. 120 hours) under the GPI program. • All tools and platforms used are on free/community tiers (MongoDB Atlas, Render, Vercel, GitHub, VS Code). • Any future production deployment costs are out of scope for this internship project.
PROJECT STAKEHOLDERS AND CUSTOMERS
PROCESS OWNER (Mention the Project Owner) | Cloud Counselage Full‑Stack Domain Lead / Project Manager – Harshada Topale
KEY STAKEHOLDERS (Mention all the stake holders involved in the project.) | • Project Sponsor – Tushar Topale (Cloud Counselage) • Project Manager / Domain Lead – Harshada Topale (Cloud Counselage) • Intern / Developer – Anuj Tiwari • GPI Program Coordinators and Evaluation Team • Partner organisations and recruiters who may use PathPort in future • Higher‑education students (end users)
END CUSTOMER (Mention the client name.) | Primary: Higher‑education students looking for continuous professional development. Secondary: Recruiting organisations and mentors connected through the GPI / Cloud Counselage ecosystem.
PROJECT RISKS, CONSTRAINTS, ASSUMPTIONS
RISKS (Risk is any unexpected event that can affect your project — for better or for worse. Risk can affect anything: people, processes, technology, and resources.) | • Time risk – limited 120‑hour internship window, possible delays due to exams or other commitments. • Technical risk – issues in integrating external services (MongoDB Atlas, Render, Vercel, OpenAI). • AI usage risk – OpenAI rate limits or API key quota errors affecting Jarvis/Career Translator features. • Data risk – accidental exposure of credentials if .env is not handled properly. • Requirement risk – scope creep if too many features are added beyond initial plan.
ASSUMPTIONS (An assumption is any project factor that is considered to be true, real, or certain without empirical proof or demonstration.) | • Stable internet connection is available for development, testing and deployment. • Free tiers of MongoDB Atlas, Render and Vercel are sufficient for this project. • GPI mentors are available for periodic feedback and clarifications. • Only one active developer (intern) works on the codebase at a time. • Evaluators will use the provided demo accounts for testing the main flows.
CONSTRAINTS (Project constraints are anything that restricts or dictates the actions of the project team.) | • Technology constraint – Project must be implemented using the MERN stack as per GPI guidelines. • Cost constraint – Only free and open‑source tools/platforms can be used; no paid licences. • Time constraint – Approximately 120 hours within the official internship dates. • Security constraint – Cannot expose real secret keys or database URIs in the source code or public repo. • Scope constraint – Focus on web application only; no native mobile app or advanced analytics in this phase.
MILESTONES
MILESTONE 1- Requirement Gathering ("Mention Completion Date in MM-DD-YYYY format. Requirement gathering is marked as complete after submission of SRS document") | 04-20-2026
MILESTONE 2 - Planning ("Mention Completion Date in MM-DD-YYYY format. Planning phase is considered after a duly completed Work Breakdown Structure (WBS), Project Schedule and RAID logs") | 04-22-2026
MILESTONE 3 - Design ("Mention Completion Date in MM-DD-YYYY format. Design stage is considered complete after submission of Design Specifications and Wireframe files") | 04-29-2026
MILESTONE 4 - Development ("Mention Completion Date in MM-DD-YYYY format. Development stage is considered complete after submission of Design Specifications and Wireframe files") | 04-29-2026
MILESTONE 5 - Testing ("Mention Completion Date in MM-DD-YYYY format. Testing stage is considered complete after submission of Test Reports") | 04-30-2026
MILESTONE 6 - Deployment ("Mention Completion Date in MM-DD-YYYY format. Deployment stage is considered complete after sybmitting the ") | 04-30-2026
MILESTONE 7 - Closure ("Mention Completion Date in MM-DD-YYYY format. Project closure is considered complete after handover of leasson learnt log, project report and installation guide") | 2026-04-05