## Sheet1
IAC Internship Program 2026 – Full Stack Web Development (MERN) Project Schedule
Project Name:- PathPort – Professional Networking Platform for Higher Education Students
PROJECT MANAGER:- Harshada Topale
Submitted by:- Anuj Tiwari
Internship Id:- IP-11182
PROJECT DELIVERABLE:- PathPort MERN Web Application (Job, Mentorship & Networking Portal for Students, Recruiters & Mentors)
PROJECT SCOPE:- Build a job portal with student, recruiter and mentor modules with AI features
PROJECT START DATE:- 20-Apr-2026
PROJECT END DATE:- 04-May-2026
OVERALL PROGRESS:- Completed
Sr No | Week/ Duration/ Sprint/ Phase | Activities | Task | Sub Task | Dependencies | Assigned to | Start Date | End Date | Actual End Date | Total Hours | Status | Progress
1 | Initiation
1.1 |  | Business Analysis | Identify business problem |  | None | Anuj Tiwari | 2026-04-20 | 2026-04-20 | 2026-04-20 | 4 | COMPLETED | 100%
1.2 |  | Requirement Analysis | Requirement gathering |  | 1.1 | Anuj Tiwari | 2026-04-20 | 2026-04-21 | 2026-04-21 | 6 | COMPLETED | 100%
1.3 |  | Documentation | Create project charter |  | 1.2 | Anuj Tiwari | 2026-04-21 | 2026-04-21 | 2026-04-21 | 4 | COMPLETED | 100%
1.4 |  | Documentation | Requirement documentation (SRS) |  | 1.3 | Anuj Tiwari | 2026-04-21 | 2026-04-22 | 2026-04-22 | 6 | COMPLETED | 100%
2 | Planning
2.1 |  | Planning | Approval of business process |  | 1.4 | Anuj Tiwari | 2026-04-22 | 2026-04-23 | 2026-04-23 | 6 | COMPLETED | 100%
2.2 |  | Planning | Baseline project plan |  | 2.1 | Anuj Tiwari | 2026-04-22 | 2026-04-23 | 2026-04-23 | 6 | COMPLETED | 100%
2.3 |  | Planning | Team roles and responsibilities |  | 2.2 | Anuj Tiwari | 2026-04-23 | 2026-04-24 | 2026-04-24 | 6 | COMPLETED | 100%
3 | Execution
3.1 |  | Design | Finalize design |  | 2.3 | Anuj Tiwari | 2026-04-23 | 2026-04-25 | 2026-04-25 | 8 | COMPLETED | 100%
3.2 |  | Development | Build |  | 3.1 | Anuj Tiwari | 2026-04-25 | 2026-05-01 | 2026-05-01 | 24 | IN PROGRESS | 90%
3.2.1 |  | Development | Features | Registration of candidate and employer | 3.2 | Anuj Tiwari | 2026-04-25 | 2026-04-26 | 2026-04-26 | 4 | COMPLETED | 100%
|  | Development |  | Login for candidate and employer | 3.2.1 | Anuj Tiwari | 2026-04-25 | 2026-04-26 | 2026-04-26 | 4 | COMPLETED | 100%
|  | UI | Home page layout | Navigation bar with logo | 3.2.1 | Anuj Tiwari | 2026-04-26 | 2026-04-27 | 2026-04-27 | 4 | COMPLETED | 100%
|  | UI |  | Home | 3.2.1 | Anuj Tiwari | 2026-04-26 | 2026-04-27 | 2026-04-27 | 4 | COMPLETED | 100%
|  | UI |  | Jobs | 3.2.1 | Anuj Tiwari | 2026-04-27 | 2026-04-28 | 2026-04-28 | 4 | COMPLETED | 100%
|  | Module | Candidates | List of candidates with information | 3.2.1 | Anuj Tiwari | 2026-04-27 | 2026-04-28 | 2026-04-28 | 4 | COMPLETED | 100%
|  | Module | Employer | List of employers with information | 3.2.1 | Anuj Tiwari | 2026-04-28 | 2026-04-29 | 2026-04-29 | 4 | COMPLETED | 100%
|  | Feature | Advance search bar | Keyword | 3.2.1 | Anuj Tiwari | 2026-04-29 | 2026-04-29 | 2026-04-29 | 3 | COMPLETED | 100%
|  | Feature |  | Upload resume | 3.2.1 | Anuj Tiwari | 2026-04-29 | 2026-04-30 | 2026-04-30 | 4 | COMPLETED | 100%
|  | Feature |  | Job categories | 3.2.1 | Anuj Tiwari | 2026-04-30 | 2026-04-30 | 2026-04-30 | 3 | COMPLETED | 100%
|  | Module | Job listing / Job result page | Employer name | 3.2.1 | Anuj Tiwari | 2026-04-30 | 2026-05-01 | 2026-05-01 | 4 | COMPLETED | 100%
|  | Module |  | Job category & type | 3.2.1 | Anuj Tiwari | 2026-04-30 | 2026-05-01 | 2026-05-01 | 4 | COMPLETED | 100%
|  | Module |  | Date & location | 3.2.1 | Anuj Tiwari | 2026-04-30 | 2026-05-01 | 2026-05-01 | 4 | COMPLETED | 100%
|  | Module |  | Favorite | 3.2.1 | Anuj Tiwari | 2026-05-01 | 2026-05-01 | 2026-05-01 | 3 | COMPLETED | 100%
|  | Feature | Apply filter & sort |  | 3.2.1 | Anuj Tiwari | 2026-05-01 | 2026-05-01 | 2026-05-01 | 3 | COMPLETED | 100%
|  | Process | Apply for job | Employer information | 3.2.1 | Anuj Tiwari | 2026-05-01 | 2026-05-02 | 2026-05-02 | 4 | COMPLETED | 100%
|  | Process |  | Deadline of application | 3.2.1 | Anuj Tiwari | 2026-05-01 | 2026-05-02 | 2026-05-02 | 4 | COMPLETED | 100%
|  | Process |  | Job details | 3.2.1 | Anuj Tiwari | 2026-05-01 | 2026-05-02 | 2026-05-02 | 4 | COMPLETED | 100%
|  | Process |  | Job description | 3.2.1 | Anuj Tiwari | 2026-05-01 | 2026-05-02 | 2026-05-02 | 4 | COMPLETED | 100%
|  | Process |  | Role | 3.2.1 | Anuj Tiwari | 2026-05-01 | 2026-05-02 | 2026-05-02 | 4 | COMPLETED | 100%
|  | Process |  | Required skills | 3.2.1 | Anuj Tiwari | 2026-05-01 | 2026-05-02 | 2026-05-02 | 4 | COMPLETED | 100%
|  | UI | Footer | Quick links for candidate & employer | 3.2.1 | Anuj Tiwari | 2026-05-02 | 2026-05-02 | 2026-05-02 | 3 | COMPLETED | 100%
|  | UI |  | Legal and company information | 3.2.1 | Anuj Tiwari | 2026-05-02 | 2026-05-02 | 2026-05-02 | 3 | COMPLETED | 100%
|  | UI |  | Social media follow | 3.2.1 | Anuj Tiwari | 2026-05-02 | 2026-05-02 | 2026-05-02 | 3 | COMPLETED | 100%
|  | Module | Profile | Dashboard | 3.2.1 | Anuj Tiwari | 2026-05-02 | 2026-05-03 | 2026-05-03 | 4 | COMPLETED | 100%
|  | Module |  | Job alerts | 3.2.1 | Anuj Tiwari | 2026-05-02 | 2026-05-03 | 2026-05-03 | 4 | COMPLETED | 100%
|  | Module |  | Applied jobs / posted jobs | 3.2.1 | Anuj Tiwari | 2026-05-02 | 2026-05-03 | 2026-05-03 | 4 | COMPLETED | 100%
|  | Module |  | Favorite jobs / candidates | 3.2.1 | Anuj Tiwari | 2026-05-02 | 2026-05-03 | 2026-05-03 | 4 | COMPLETED | 100%
|  | Process | Post job | Job title and description | 3.2.1 | Anuj Tiwari | 2026-05-03 | 2026-05-03 | 2026-05-03 | 3 | COMPLETED | 100%
|  | Process |  | Job category and type | 3.2.1 | Anuj Tiwari | 2026-05-03 | 2026-05-03 | 2026-05-03 | 3 | COMPLETED | 100%
|  | Process |  | Required skills & deadline | 3.2.1 | Anuj Tiwari | 2026-05-03 | 2026-05-03 | 2026-05-03 | 3 | COMPLETED | 100%
|  | Process |  | Salary and qualification | 3.2.1 | Anuj Tiwari | 2026-05-03 | 2026-05-03 | 2026-05-03 | 3 | COMPLETED | 100%
|  | Process |  | Location | 3.2.1 | Anuj Tiwari | 2026-05-03 | 2026-05-03 | 2026-05-03 | 3 | COMPLETED | 100%
3.3 |  | Testing | Testing & Bug Fixing |  | 3.2 | Anuj Tiwari | 2026-05-03 | 2026-05-04 | 2026-05-04 | 8 | COMPLETED | 100%
3.3.1 |  | Testing | Manual testing |  | 3.3 | Anuj Tiwari | 2026-05-03 | 2026-05-04 | 2026-05-04 | 4 | COMPLETED | 100%
3.3.2 |  | Testing | Automation testing |  | 3.3 | Anuj Tiwari | 2026-05-03 | 2026-05-04 | 2026-05-04 | 4 | COMPLETED | 100%
4 | Closure
4.1 |  | Deployment | Project closure & deployment |  | 3.3 | Anuj Tiwari | 2026-05-04 | 2026-05-04 | 2026-05-04 | 4 | COMPLETED | 100%
Note on H15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Nirbhey Singh Pahwa - I was thinking if we should add an actual start date column as well? Reply: Or, let's call this one as planned start date and the next one as start date. The same can be done for End date. Because, writing 'actual' feels as if we've missed some deadline of some sorts so can be avoided. You can have this in the DM Goals template for now, let me add this to the next version of this template, i.e., Goals [Template v0.5] Thank you