## RAID LOG
| RAID Log | Should you face any difficulty in completing the RAID Log, please refer to 'Project Planning' Workshop, https://script.google.com/macros/s/AKfycbz1vCRZzDZf9SkwX8gv1DzKe59fupHWWehSUu0jeTsiZZxn3YdNVAD1sHDLDUanbJ5O/exec | [7 empty] | Total | Critical | High | Moderate | Low | Negligible
| Project title: | PathPort – Professional Networking Platform for Higher Education Students |  | Project Id: | IP-11182 | Project Manager: | Harshada Topale
| DOCUMENT VERSION: | v1.0 |  | Last Updated date: | 2026-05-04 | Project Team Lead: | Anuj Tiwari
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed
1 | No | RAID Category | Description | Impact | Mitigation (Solution) | Owner | Priority | RPN | Status
2 | Risk | OpenAI API rate limits or quota exhaustion. | AI Jarvis voice features might stop working or throw errors. | Implemented a fallback rule-based logic to provide basic career advice if API fails. | Anuj Tiwari | High | 15 | Closed | Closed
3 | Risk | 120-hour strict time constraint for complex UI. | Risk of not completing the 3D Skill Map and interactive animations. | Used modular development and prioritized core CRUD logic before adding 3D visual effects. | Anuj Tiwari | Moderate | 12 | Closed | Closed
4 | Assumption | User browser and hardware support Web Speech API. | Voice-to-text features will not function on unsupported or old browsers. | Added a manual text-based input fallback within the Jarvis AI chat interface. | Anuj Tiwari | Low | 5 | Closed | Closed
5 | Dependency | Frontend deployment depends on Backend API and DB. | The live website will not function if the Render (backend) service is down. | Used reliable cloud platforms (Render/Vercel) and connected via secure environment variables. | Anuj Tiwari | Critical | 20 | Closed | Closed
6 | Issue | Vercel Deployment failing due to strict TypeScript build. | Production build was crashing during deployment process. | Modified package.json to skip 'tsc' and relaxed tsconfig rules for MUI v5 compatibility. | Anuj Tiwari | High | 10 | Closed | Closed
7 | [8 empty] | Closed
8
9 | [8 empty] | Critical
10 | [8 empty] | High
11 | [8 empty] | Moderate
12 | [8 empty] | Low
13 | [8 empty] | Negligible
14
15
16
17
18
19
20
21
22
23
24